## Sheet1
Date | Reporter | Description | Fix date | Who fixed it | How fixed
2022-04-20 | Liam | Barbarian flavor text gives undefined after a few turns | 2022-04-20 | Liam | Checked to reset flavor tracker after incrementing it
2022-04-20 | Matt | html file not loading overworld | 2022-04-20 | Matt | some js imports were typed incorrectly in some files causing the file to not load
2022-04-21 | Liam | Player HP bar always starts full, even if player not at full hp | 2022-04-23 | Liam | Added call to setPlayerHealth at start of BattleScene
2022-04-23 | Matt | Battle scene reset the overworld when battle ended | 2022-04-23 | Matt | added a function in the enemy prototype that indexed the levels depending on which enemy you just battled
2022-04-24 | Liam | Move descriptions still appeared during stats section of level up | 2022-04-24 | Liam | Destroyed move objects and cancelled the event that handled descriptions
2022-04-24 | Mitchell | Coin flip mostly results in heads
2022-04-24 | Mickey | Music does not always start at the beginning of the game