## Sheet1
| 1 | 2 | 3 | 5 | 8 | 13 | 20+
references | Hello World Program | JS Pie Chart | Circle Comparator | Complexity Lab | Shapes Container | maze solver
| Make A Restaurant Receipt Using Command Line Input | check for overlapping ships | Board Games | 388 final module 2 | Web Search Using Linked List | pokemon database
| File I/O Practice | convert ships to tile arrays | JS Tabs | drawGrid | 388 final module 3 | 388 final project module 1 + reverse
| Project 2 implementation of different shots | Create big shot function | AI ship placement | Player object (x2) | Project 2 Medium AI
|  | make Opponent Interface | implement shot selection UI | Barbarian object | Battle UI
|  | Enemy prototype |  | battle level creation | Overworld
stories
|  | Sprite creation |  | Move pool | Exapnd Overworld | Create Level up UI
Game balance
More enemies
points to hours conversion: | 0.75 hours/story point | estimated using time we took to complete low point stories, used higher point stories as sanity check
| 0 | 1 | 0 | 1 | 1 | 1
| 0 | 0 | 0 | 0 | 1 | 0
| 0 | 0 | 0 | 0 | 1 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
Total story points estimate | 44
Total hours estimate | 33